## Project timeline
AmanID Project Team Members : Razan Aljelaify - Nora Alhuwaidi - Nora Altuwaim - Layan Aldaghfaq
Start Date: | 2023-03-26
Tasks this week : | Week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | Status:
| Mar | [6 empty] | Mar | [6 empty] | Mar-Apr | [6 empty] | Apr
| Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
| 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07
| 1900-01-11: Link Android Studio with GitHub + | Complete
| 1900-01-11: Create a new Repository + Add team Members | Complete
| 1900-01-17: Start to Develop The XML Interfaces + Link the Interfaces with each other | completed
Tasks this week : | 1900-01-11: week 5; 1900-01-18: week 6; 1900-01-25: week 7; 1900-02-01: week 8
| Apr | [6 empty] | may | [6 empty] | may | [6 empty] | may
| Sun | Mon | Tue | Thu | Fri | Sat | Sun | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
| 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04
| 1900-01-08: Create a new Repository for the website; 1900-01-15: Continue to develop and fix errors; 1900-01-24: REFACTORING & ERROR HANDLING; 1900-01-29: Link our app with FB | completed
| 1900-01-08: Link The Firebase + creat website; 1900-01-15: Apply API; 1900-01-24: Designing; 1900-01-29: Add Sumilator Bank & Link | completed
| week 9 | [6 empty] | week 10 | [6 empty] | week 11 | [6 empty] | week 12
Tasks this week : | 1900-01-08: May; 1900-01-15: May; 1900-01-22: May; 1900-01-29: May
| Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-05-21 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-01-01 | 1900-01-02
| May Mon: Continue to develop and fix errors; May Wed: REFACTORING & ERROR HANDLING; May Mon: Set History for Transaxtions | completed
| May Mon: Apply API; May Wed: SetUp Localhost; May Mon: Link all Transactions with FB | completed
| May Mon: TESTING | in progress