## Project timeline
AmanID Project Team Members : Razan Aljelaify - Nora Alhuwaidi - Nora Altuwaim - Layan Aldaghfaq
Start Date: | 2023-03-26
Tasks this week : | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | Status:
| mar | [6 empty] | apr | [6 empty] | apr | [6 empty] | apr
| sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat
| 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22
| 2023-03-26: Link Android Studio with GitHub + | Complete
| 2023-03-26: Create a new Repository + Add team Members | Complete
Start to Develop The XML Interfaces + Link the Interfaces with each other
Tasks this week : | 2023-03-26: week 5; 2023-04-02: week 6; 2023-04-09: week 7; 2023-04-16: week 8
| may | [6 empty] | may | [6 empty] | may | [6 empty] | may
| sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri
| 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26
| 0: Create a new Repository for the website; 1900-01-06: Continue to develop and fix errors | in progress
| Link The Firebase + creat website | [6 empty] | Apply API
Tasks this week : | 0: week 9
jan
| sun | mon | tue | wed | thu | fri | sat
| 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06